## Bug Tracking
# | Bug ID | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Reference document folder | Reported By | Assigned to | Reported Date | Last Changed Date | Status
1 | OCD0001 | User is able to register an account by providing an invalid Telephone number | 1. Click on 'My Account' dropdown menu 2. Click on 'Register' option 3. Enter new account details into all fields(First Name, Last Name, Email, Password, Password Confirm, Newsletter, privacy policy) 4. Key in the invalid Telephone number. < Test data: 98111111A$ > 4. Click on 'Continue' button | Proper field level warning message should be displayed and account should not be created. | Warning message is not getting displayed and user account is getting created with invalid Telephone number | Major | P2 | \Bug Reporting Documents\OCD0001
2 | OCD0002 | User is not automatically getting logged out of the application after 10 minutes of inactivity | 1. Click on 'My Account' drop down menu 2. Click on 'Login' option 3. Enter valid email address into the 'E-Mail Address' field - <Refer Test Data> 4. Enter valid password into the 'Password' field - <Refer Test Data> 5. Click on 'Login' button 6. Wait for more than 10 minutes without performing any activity on the application 7. Perform any action on the application | User should get automatically logged out with a proper message stating your session got expired. | User is not getting automatically logged out with a proper message stating your session got expired. | Minor | P2 | \Bug Reporting Documents\OCD0002
3
4
5
6
7
8
9
10
11
12
13
14
15

## Notes
Severity Types | Meaning
Critical (High) | Blocker- no further testing can be done
Major (Medium) | Functionality is affected
Minor (Low) | Functionality not affect, Issue with UI or some undesired behavior
Priority Types | Meaning
P0 | High
P1 | Medium
P2 | Low